## Workplan Chart
PhD MSMF WORKPLAN CHART AND TIMELINE
WORKSTREAM / TASK | STATUS / MILESTONE | YEAR 0 (2026) |  |  | YEAR 1 (2027) | [11 empty] | YEAR 2 (2028) | [11 empty] | YEAR 3 (2029) | [11 empty] | YEAR 4 (2030)
|  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
PRE-APPLICATION MANUSCRIPT WORK
BCR reconstruction and QC: GSE166780 + GSE173983 | Ongoing | bar: YEAR 0 (2026) Oct
TRUST4 / MiXCR comparison and repertoire analyses beyond bcRflow | Ongoing | bar: YEAR 0 (2026) Oct
Antigen-dependent analysis and candidate prioritisation | Planned | bar: YEAR 0 (2026) Nov
AlphaFold-Multimer pilot and structural interpretation | Planned | bar: YEAR 0 (2026) Nov
Tissue dataset analysis and manuscript consolidation | Planned | bar: YEAR 0 (2026) Dec
APPLICATION AND ADMISSION
PhD application — January | A | bar: YEAR 1 (2027) Jan
Admission presentation | AP | bar: YEAR 1 (2027) Jan to YEAR 1 (2027) Feb
PROPOSAL AND REGISTRATION
Form DAC and prepare 10–15 page proposal | Planned | bar: YEAR 1 (2027) Feb to YEAR 1 (2027) May
Submit Manuscript 1: public blood/tissue data (Aim 2A) | M1 | bar: YEAR 1 (2027) Mar to YEAR 1 (2027) Aug
MSMF protocol presentation to DAC | P1 | bar: YEAR 1 (2027) Jun
Respond to DAC comments and collect signatures | 7d | bar: YEAR 1 (2027) Jun
Submit proposal to MAHE; MAHE PPAC / registration | P2 | bar: YEAR 1 (2027) Jul to YEAR 1 (2027) Aug
DAC 1: report of MAHE presentation | D1 | bar: YEAR 1 (2027) Sep
YEAR 1: SEP 2027–AUG 2028
Complete 12 coursework credits | Planned | bar: YEAR 1 (2027) Sep to YEAR 2 (2028) Feb
Obtain ethics approval for Aim 2B before recruitment - PARALLEL to AIM A | E | bar: YEAR 1 (2027) Sep to YEAR 2 (2028) Feb
Extend public-data analysis: tissue vs PBMC; stable vs advanced disease | Planned | bar: YEAR 1 (2027) Sep to YEAR 2 (2028) Feb
Design CT calcium score cohort study and confirm clinical partner | Planned | bar: YEAR 1 (2027) Sep to YEAR 2 (2028) Feb
Recruitment and PBMC collection (about 20 patients) | Planned | bar: YEAR 2 (2028) Mar to YEAR 2 (2028) Aug
Draft/submit review article; first conference/poster | R1 | bar: YEAR 2 (2028) Mar to YEAR 2 (2028) Aug
YEAR 3: SEP 2028–AUG 2029
Finish recruitment; RNA extraction, QC, library preparation and RNA-seq | Planned | bar: YEAR 2 (2028) Sep to YEAR 3 (2029) Feb
Optional antigen-dependent / AlphaFold analysis on selected candidates | Planned | bar: YEAR 2 (2028) Sep to YEAR 3 (2029) Feb
DAC 2–5: six-monthly presentations and progress reports | D2–D5 | YEAR 2 (2028) Mar: D2–D5
Second conference/poster presentation | C2 | bar: YEAR 3 (2029) Mar to YEAR 3 (2029) Aug
BCR reconstruction and repertoire analysis of new RNA-seq | Planned | bar: YEAR 3 (2029) Mar to YEAR 3 (2029) Aug
Explore repertoire associations with CT calcium score | Planned | bar: YEAR 3 (2029) Mar to YEAR 3 (2029) Aug
YEAR 3: SEP 2029–AUG 2030
Submit Manuscript 2 (Aim 2B); thesis writing alongside papers | M2 | bar: YEAR 3 (2029) Sep to YEAR 4 (2030) Feb
Grant concept note / wider blood-based prognostic study | Planned | bar: YEAR 3 (2029) Sep to YEAR 4 (2030) Feb
DAC 6: seek permission for open synopsis presentation | D6 | bar: YEAR 4 (2030) Mar
Open synopsis presentation | S | bar: YEAR 4 (2030) Mar to YEAR 4 (2030) Aug
Turnitin report (<15%) and CDS NOC | NOC | YEAR 4 (2030) Jul: NOC
Thesis submission to Registrar (Evaluation) | T | bar: YEAR 4 (2030) Aug
ONGOING REQUIREMENTS
Supervisor/co-supervisor review | Planned
Two first-author papers (IF ≥3.0; MAHE affiliation) | Planned | bar: YEAR 1 (2027) Mar to YEAR 4 (2030) Aug
Progress reports to MAHE/CDS after DAC reviews | Planned | bar: YEAR 1 (2027) Sep to YEAR 4 (2030) Mar
PARKED AIM
Aim 1: agent-based model of adaptive immune response | HOLD | YEAR 1 (2027) Mar: HOLD
Note on A8: Optional small pilot; predicted structures are not proof of binding
Note on A9: Reduce tissue scope if needed to protect manuscript quality
Note on A11: Application cycle confirmed
Note on A12: Planned 26 Feb 2027; update if institution confirms another date
Note on A14: Two aims, Gantt chart, preliminary work, clinical relevance and translational outcome/IP
Note on A15: Target submission by Aug 2027
Note on A16: Coordinator ceiling: 6 months after admission presentation
Note on A17: Within 7 days after every DAC presentation
Note on A18: PPAC 4–6 weeks after proposal submission; within 2 months after MSMF presentation
Note on A19: Planned Sep 2027; within 2 weeks after PPAC
Note on A21: Within 6 months of registration; confirm conflicting guideline wording
Note on A22: Plan to 6 months after registration
Note on A23: Aim 2A
Note on A24: Aim 2B depends on access, ethics and resources
Note on A25: Only after ethics approval
Note on A26: Review may count as one required paper if guideline conditions are met
Note on A28: Aim 2B
Note on A29: Cut first if schedule is tight
Note on A30: Response within 7 days; progress report after each
Note on A31: Complete before thesis submission
Note on A32: Aim 2B
Note on A33: Exploratory only with about 20 patients
Note on A35: Two required first-author papers must be accepted/published before synopsis
Note on A36: Broad supporting activity
Note on A37: Planned Mar 2030; assumes six-monthly DACs
Note on A38: Within 6 months after DAC 6; planned Aug 2030
Note on A39: Complete before thesis submission
Note on A40: Planned Aug 2030; must satisfy minimum duration from admission/registration
Note on A42: At least monthly
Note on A43: Complete before synopsis; guide/supervisor corresponding author
Note on A44: Every 6 months; two consecutive missed reports can cancel registration
Note on A46: Tentative and on hold at supervisor's request

## Task Tracker
ID | Month | Workstream | Task / Goal | Estimated effort (days) | Status | Definition of done / deliverable | Next action / notes | Deadline type | Latest date / rule
1 | October | Planning | Audit existing analysis and freeze blood-dataset sample metadata | 2 | Not Started | Verified sample sheet, group labels, inclusion/exclusion rules | Confirm counts and conditions for GSE166780 and GSE173983 | Planned
2 | October | BCR reconstruction | Re-run reconstruction on GSE166780 | 5 | Not Started | Per-sample outputs, logs, tool versions, parameters and QC recorded | Compare rerun with existing TRUST4 and MiXCR outputs | Planned
3 | October | BCR reconstruction | Re-run reconstruction on GSE173983 | 3 | Not Started | Per-sample outputs, logs and QC recorded | Keep validation cohort separate | Planned
4 | October | Pipeline comparison | Compare TRUST4 and MiXCR reconstruction outputs | 4 | Not Started | Per-sample summary of productive contigs, chain recovery, QC and failures | Do not select a tool on total sequence counts alone | Planned
5 | October | Repertoire analysis | Run diversity/repertoire tools beyond bcRflow | 6 | Not Started | Reproducible sample-level metrics and figures for both cohorts | Assess diversity, clonality, V/J usage, CDR3 and isotype where supported | Planned
6 | October | Statistics | Create cross-dataset analysis table and statistical plan | 3 | Not Started | Master table, planned group comparisons and documented cohort limitations | GSE173983 is very small (n=4 total per documentation) | Planned
7 | October | Manuscript | Create manuscript skeleton and figure plan | 2 | Not Started | Working title, aims, Methods outline and planned figures | Keep claims proportionate to the public bulk RNA-seq cohorts | Planned
8 | November | Antigen-dependent analysis | Audit and consolidate existing antigen-dependent outputs | 3 | Not Started | Inventory of candidates, antigen list, pairing/structure status and gaps | Mark what is complete, needs rerunning, or is not reliable | Planned
9 | November | Antigen-dependent analysis | Prioritise candidate BCR/antibody sequences | 4 | Not Started | Transparent candidate-selection criteria and ranked candidate list | Clonal expansion is not by itself proof of antigen specificity | Planned
10 | November | Antigen-dependent analysis | Complete or refresh antigen-dependent analysis for selected candidates | 8 | Not Started | Reproducible candidate–antigen table and interpretable figures | Record antigen structure/provenance and uncertainty | Planned
11 | November | Structural modelling | Decide where AlphaFold/AlphaFold-Multimer may help | 3 | Not Started | Short methods decision note and pilot design | Check chain setup, antigen construct and complex confidence metrics | Planned
12 | November | Structural modelling | Run a small AlphaFold complex-modelling pilot | 5 | Not Started | Pilot structures and quality summary compared with existing docking | Predicted structures/confidence are not proof of binding | Planned
13 | November | Integration | Integrate repertoire, antigen and structural results | 4 | Not Started | Coherent tables/figures and explicit limitations | Identify strongest manuscript-level claims and remaining gaps | Planned
14 | November | Manuscript | Draft Methods and Results for blood-dataset work | 5 | Not Started | First complete draft of Methods and Results with figure references | Draft while results stabilise | Planned
15 | December | Tissue datasets | Identify suitable tissue RNA-seq datasets | 4 | Not Started | Dataset screening table: accession, tissue, sample size, phenotype, reads, metadata | Prefer a manageable dataset with useful metadata | Planned
16 | December | Tissue datasets | Download/process selected tissue data and run QC | 5 | Not Started | QC summaries and reproducible processing logs | Avoid expanding to many datasets | Planned
17 | December | Tissue BCR reconstruction | Run BCR reconstruction on selected tissue data | 6 | Not Started | Per-sample reconstruction outputs and comparable QC metrics | Tissue and PBMC may differ in immune-cell abundance and BCR recovery | Planned
18 | December | Tissue repertoire analysis | Run diversity/clonality analyses on tissue data | 5 | Not Started | Tissue sample-level repertoire table and core figures | Reuse metric definitions where technically appropriate | Planned
19 | December | Cross-compartment | Compare tissue and blood results where valid | 4 | Not Started | Comparison with explicit cohort/protocol caveats | Avoid pooling incompatible designs | Planned
20 | December | Manuscript | Integrate findings and prepare manuscript package | 6 | Not Started | Coherent draft, core figures, methods, results and limitations for supervisor review | Reserve time for revisions and reproducibility checks | Planned
21 | All three months | Reproducibility | Maintain run log, versions, parameters, scripts and provenance | 1 | In Progress | Every reported result traceable to code, inputs and parameters | Update after each run | Planned
22 | All three months | Supervisor check-ins | Review progress, unblock decisions and agree scope cuts | 1 | Not Started | Short decision log after each check-in | Agree early on minimum manuscript-ready scope | Planned
23 | January 2027 | Manuscript | Supervisor review and revision of the pre-admission manuscript draft | 5 | Not Started | Reviewed draft with an agreed list of revisions and open claims | Keep claims proportionate to the public bulk RNA-seq data | Planned
24 | January 2027 | Application | Confirm eligibility and PI funding/interest, then email the application to the PhD office | 2 | Not Started | Application sent in the January intake; test-waiver status known | Written test is waived for staff with more than 6 months at MSMF - confirm if this applies. Send to phd.office@ms-mf.org | FIXED | January 2027 intake
25 | January 2027 | Application | Prepare the admission presentation: rationale and at least two aims (Aim 2A, Aim 2B) | 6 | Not Started | Short deck with rationale, both aims, preliminary results from the Oct-Dec work and expected outcomes | Aim 1 (agent-based model) is on hold per the supervisor; leave it out unless he asks | Planned
26 | Jan-Feb 2027 | Application | Written test, if not waived | 4 | Not Started | Test completed | Covers basic statistics, chemistry, instrumentation, cell and molecular biology. Skip if waived | Planned
27 | February 2027 (assumed) | Admission | Admission presentation to MSMF - Day 0 for all coordinator ceilings | 1 | Not Started | Presentation delivered and selection outcome received | Assumed date. Update the yellow date on Key Deadlines once MSMF confirms | FIXED | 2027-02-26
28 | Feb-Mar 2027 | Admission | Complete MAHE admission: admission order form, joining report, fee payment | 3 | Not Started | Admission order and joining report filed; fees paid | Late fee payment can cancel registration | Planned
29 | Mar-Apr 2027 | Proposal | Form the DAC (maximum 8 members, including an external clinician and a clinician from the sample source) | 3 | Not Started | DAC list agreed by the PhD coordinator and supervisor | Aim 2B needs a clinician from the sample-collection site (NH or another partner) | FIXED | 2027-08-26
30 | Mar-May 2027 | Proposal | Write the 10-15 page proposal: two aims, Gantt chart, preliminary work, clinical relevance, translational outcome/IP | 15 | Not Started | Supervisor-approved proposal in MAHE format, with Turnitin report | Needs an external funding plan and a supervisor declaration | Planned
31 | Mar-Aug 2027 | Manuscript | Submit manuscript 1 (Aim 2A, public blood and tissue data) to a journal with IF 3.0 or higher | 10 | Not Started | Manuscript submitted; first author, guide corresponding | MAHE affiliation is needed for it to count as a required paper; check with the coordinator since the work started before admission | Planned
32 | Jun 2027 (planned) | Proposal | Protocol presentation at MSMF to the DAC (1-page summary to members at least 3 days before) | 3 | Not Started | Presentation delivered; DAC comments recorded | Coordinator ceiling is 6 months after the admission presentation | FIXED | 2027-08-26
33 | Within 7 days | Proposal | Respond to DAC comments and collect signatures | 2 | Not Started | Signed response circulated to all DAC members | Applies after every DAC presentation, not just this one | FIXED | 7 days after each DAC
34 | Aug 2027 (planned) | Registration | Submit proposal and Turnitin report to MAHE, then present to the MAHE PPAC (4-6 weeks after submission) | 4 | Not Started | PPAC approval; the presentation date becomes the registration date | Submit soon after the MSMF presentation so the PPAC lands inside the 2-month ceiling | FIXED | 2027-10-26
35 | Sep 2027 (planned) | Registration | DAC 1: report on the MAHE presentation | 1 | Not Started | DAC 1 minutes filed; next DAC date set | Board ceiling is 2 weeks after the PPAC | FIXED | 2027-11-09
36 | Y1 H1 (Sep 2027-Feb 2028) | Coursework | Complete 12 credits: 6 research-specific, 4 methodology, 2 publication ethics | 24 | Not Started | Transcript and comprehensive grade sheet | One credit is 16 learning hours. Missing the deadline cancels registration | FIXED | 2028-02-26
37 | Y1 H1 (Sep 2027-Feb 2028) | Ethics | Ethics approval for Aim 2B patient samples and data (IBSC only if recombinant DNA is involved) | 10 | Not Started | Approvals in hand before any recruitment | Guidelines say 6 months in one place and 1 year in another; plan to 6 months | FIXED | 2028-02-26
38 | Y1 H1 (Sep 2027-Feb 2028) | Aim 2A | Extend public-data analysis: tissue vs PBMC, and stable vs advanced disease, for antigen-independent and antigen-specific features | 40 | Not Started | Comparative results with caveats; patterns that separate stable from advanced | Reuse the Oct-Dec pipeline; compare only compatible study designs | Planned
39 | Y1 H1 (Sep 2027-Feb 2028) | Aim 2B | Design the CT calcium score study: clinical partner, mild (1-99) vs advanced (299 or more) criteria, n about 20, consent, sequencing plan | 20 | Not Started | Study protocol, partner agreement and sample-handling SOPs | Settle NH or another partner early; everything in Aim 2B depends on it | Planned
40 | Y1 H1 (Sep 2027-Feb 2028) | Manuscript | Respond to reviewer comments on manuscript 1 and resubmit if needed | 10 | Not Started | Revised manuscript and response letter | Timing depends on the journal | Planned
41 | Y1 H2 to Y2 H2 (Mar 2028-Aug 2029) | DAC cycle | DAC 2-5: six-monthly DAC presentation, response within 7 days, and progress report to MAHE after each | 12 | Not Started | Four DAC meetings with minutes, each followed by a MAHE progress report | Two consecutive missed reports cancels registration. Reports are 10-12 pages with DAC recommendation and coursework status | FIXED | 2029-11-09
42 | Y1 H2 (Mar-Aug 2028) | Aim 2B | Start recruitment and PBMC collection (about 20 patients, mild vs advanced) | 60 | Not Started | Banked PBMC samples with clinical metadata and calcium scores | Recruitment pace is the main schedule risk; start only after ethics approval | Planned
43 | Y1 H2 (Mar-Aug 2028) | Publications | Draft a review article on BCR repertoires in atherosclerosis | 25 | Not Started | Review submitted | Can count as one of the two required papers, which protects the schedule if Aim 2B runs late | Planned
44 | Y1 H2 (Mar-Aug 2028) | Conferences | First conference or poster presentation | 5 | Not Started | Presentation certificate | Two are needed before thesis submission | Planned
45 | Y2 H1 (Sep 2028-Feb 2029) | Aim 2B | Finish recruitment; RNA extraction, QC and library preparation | 40 | Not Started | All samples collected; RNA QC records | Agree in-house vs vendor sequencing early | Planned
46 | Y2 H1 (Sep 2028-Feb 2029) | Aim 2B | RNA-seq of the PBMC samples | 20 | Not Started | Raw reads with QC | Funding for sequencing comes from the external grant plan | Planned
47 | Y2 H1 (Sep 2028-Feb 2029) | Antigen-dependent analysis | Optional: antigen-dependent and AlphaFold analysis on selected candidates from Aim 2A | 30 | Not Started | Candidate-antigen table and figures with limitations | Cut first if time is short | Planned
48 | Y2 H2 (Mar-Aug 2029) | Aim 2B | BCR reconstruction and repertoire analysis of the new RNA-seq, using the validated pipeline | 40 | Not Started | Per-patient repertoire metrics and QC | Reuse the tool decisions from the Oct-Dec comparison | Planned
49 | Y2 H2 (Mar-Aug 2029) | Aim 2B | Association of repertoire properties (diversity, clonality, isotype, V/J, CDR3) with CT calcium score | 30 | Not Started | Exploratory associations with effect sizes and caveats | About 20 patients supports exploratory findings, not definitive claims | Planned
50 | Y2 H2 (Mar-Aug 2029) | Conferences | Second conference or poster presentation | 5 | Not Started | Presentation certificate |  | Planned
51 | Y3 H1 (Sep 2029-Feb 2030) | Manuscript | Write and submit manuscript 2 (Aim 2B) | 40 | Not Started | Submitted manuscript | Acceptance before the synopsis is tight; manuscript 1 plus the review is the fallback pair | Planned
52 | Y2 H2 to Y3 H1 (Mar 2029-Feb 2030) | Thesis | Write thesis chapters alongside the papers | 60 | Not Started | Full thesis draft reviewed by the supervisor | Start early; chapters can follow the papers | Planned
53 | Y3 H1 (Sep 2029-Feb 2030) | Grant | Groundwork for a grant proposal and a wider blood-based prognostic study | 10 | Not Started | Short concept note with preliminary data | From the aims slide | Planned
54 | Mar 2030 (planned) | Completion | DAC 6: seek permission for the open synopsis presentation (all DAC members present) | 2 | Not Started | DAC approval to present the synopsis | Needs at least 6 progress reports. Date assumes six-monthly DACs; confirm with the coordinator | FIXED | 2030-05-09
55 | Before the synopsis | Publications | Two first-author publications (IF 3.0 or higher, MAHE affiliation, guide corresponding) published or accepted | 0 | Not Started | Acceptance letters or reprints | One may be a review. Effort is counted in the writing tasks above | FIXED | 2030-11-09
56 | Mar-Aug 2030 | Completion | Incorporate DAC suggestions and give the open synopsis presentation | 10 | Not Started | Synopsis approved by the DAC | Board ceiling is 6 months after DAC 6 | FIXED | 2030-11-09
57 | Before thesis submission | Conferences | Two conference or poster presentations completed with evidence | 0 | Not Started | Certificates or reprints | DAC may waive this with patents and more than two papers | FIXED | 2030-11-16
58 | Aug 2030 (planned) | Completion | Turnitin report (similarity under 15%) and CDS NOC after dues clearance | 5 | Not Started | Report and NOC in hand | Start the NOC paperwork before the synopsis | FIXED | 2030-11-16
59 | Aug 2030 (planned) | Completion | Submit the thesis to the Registrar (Evaluation) | 3 | Not Started | Thesis submitted | Not before 3 years from registration and 3.5 years from admission. Board ceiling is 7 days after the synopsis | FIXED | 2030-11-16
60 | After submission | Completion | Examiner evaluation, public defense and viva; degree at the next convocation | 0 | Not Started | Degree awarded | Two examiners; timing is outside your control | Planned
61 | 2027-2030 | Parked | Aim 1: agent-based model of the adaptive immune response (tentative) | 0 | On Hold | Decide at a later DAC whether it has a place | Supervisor asked to keep this aside for now | Planned
62 | All years | Supervisor check-ins | Supervisor and co-supervisor review of the research | 1 | Not Started | Short decision log after each review | Guidelines require review at least once a month | FIXED | Monthly

## Key Deadlines
Fixed deadlines and milestone dates
Admission presentation date (ASSUMED - edit when MSMF confirms) | 2027-02-26 | Everything below recalculates from these dates. Only the yellow cells are inputs.
MSMF protocol presentation - planned (overwrite with the real date) | 2027-06-26
MAHE PPAC presentation = registration date - planned (overwrite with the real date) | 2027-08-26
Milestone | Source | Rule | Planned date | Latest date | Notes
Admission presentation (Day 0) | Coordinator board | Start of every ceiling below | 2027-02-26 | 2027-02-26 | Assumed date; the PhD office sets the real one.
Protocol presentation at MSMF; DAC formed | Coordinator board | At most 6 months after the admission presentation | 2027-06-26 | 2027-08-26 | Circulate a 1-page summary to the DAC at least 3 days before. Respond to comments within 7 days.
Protocol presentation at MAHE (PPAC) = registration date | Coordinator board; guidelines 8.3.3 | At most 2 months after the MSMF presentation | 2027-08-26 | 2027-10-26 | MAHE schedules the PPAC 4-6 weeks after you submit, so submit soon after the MSMF presentation.
DAC 1 - report of the MAHE presentation | Coordinator board | At most 2 weeks after the PPAC | 2027-09-09 | 2027-11-09
DAC 2 | Coordinator board; guidelines 9.2 | Every 6 months from DAC 1 | 2028-03-09 | 2028-05-09 | Each DAC is followed by a progress report to MAHE (CDS).
DAC 3 | Coordinator board; guidelines 9.2 | Every 6 months | 2028-09-09 | 2028-11-09
DAC 4 | Coordinator board; guidelines 9.2 | Every 6 months | 2029-03-09 | 2029-05-09
DAC 5 | Coordinator board; guidelines 9.2 | DAC 2-5 within 2 years of DAC 1 | 2029-09-09 | 2029-11-09 | The board shows 2 years against "DAC 2-5".
DAC 6 - permission for the open synopsis presentation | Coordinator board; guidelines 10.1 | Sixth DAC meeting; at least 6 progress reports | 2030-03-09 | 2030-05-09 | TO CONFIRM: assumes DAC 6 comes 6 months after DAC 5. If the board's 2 years runs DAC 1 to DAC 6, the latest date is 6 months earlier.
Open synopsis presentation (all DAC members present) | Coordinator board | At most 6 months after DAC 6 | 2030-08-09 | 2030-11-09 | Publications must be accepted or published first.
Thesis submission | Coordinator board; guidelines 3 | At most 7 days after the synopsis, and not before the minimum duration | 2030-08-26 | 2030-11-16 | A 2-month grace period applies after the due date only if no extension was taken.
Earliest thesis submission (minimum duration) | MSMF/MAHE guidelines section 3 | At least 3 years from registration AND 3.5 years from admission | 2030-08-26 | 2030-08-26 | Full-time candidates. Extensions need DAC recommendation and university approval.
Maximum duration | MSMF/MAHE guidelines section 3 | At most 6 years from registration (full-time) |  | 2033-08-26 | Registration is cancelled if the thesis is not submitted by then.
Coursework: 12 credits | MSMF/MAHE guidelines 9.1.1, 9.4 | Within 6 months of registration | 2028-01-26 | 2028-02-26 | 6 research-specific, 4 methodology, 2 publication ethics. Missing it cancels registration. (Section 9.1 elsewhere says before registration - confirm.)
Ethics approval for patient samples/data (Aim 2B) | MSMF/MAHE guidelines 8.1.3 and 5 | Within 6 months of registration (section 5 says 1 year) | 2028-01-26 | 2028-02-26 | Plan to the stricter 6 months. IBSC approval only if recombinant DNA is involved.
Response to DAC comments | MSMF/MAHE guidelines 8.3.1, 9.2 | Within 7 days of each DAC presentation |  |  | Signatures: guide, co-guide, coordinator, experts, chairman.
Progress report to MAHE (CDS) | MSMF/MAHE guidelines 9.2, 9.4 | Every 6 months; two consecutive misses cancel registration |  |  | Maximum 10-12 pages, with DAC recommendation and coursework status.
Two first-author publications (IF 3.0 or higher) | MSMF/MAHE guidelines 9.3.1 | Published or accepted before the synopsis; MAHE affiliation; guide corresponding author | 2030-03-09 | 2030-11-09 | One may be a review article.
Two conference or poster presentations | MSMF/MAHE guidelines 9.3.2 | Before thesis submission (DAC may waive with patents and more than two papers) | 2030-08-09 | 2030-11-16 | Keep the certificates.
Turnitin report (similarity under 15%) and CDS NOC | MSMF/MAHE guidelines 10 | Before submission to the Registrar (Evaluation) | 2030-08-09 | 2030-11-16 | NOC follows dues clearance.
Check: does the board chain reach the minimum duration? |  |  |  | OK | OK means the board's ceilings run at least as late as the earliest allowed thesis date, so the two sets of rules do not contradict each other.
Red = fixed deadline (latest date). Amber = fixed but needs confirming. Planned dates are suggestions that leave room before the ceilings.
Formulas:
Planned date = [Planned date, row above]+14
Planned date = EDATE([Planned date, row above],5)
Latest date = EDATE([Latest date, row above],2)
Latest date = [Latest date, row above]+14

## Monthly Overview
PhD Roadmap: October 2026 to 2030 (months after December are broad and assume the dates on Key Deadlines)
Month | Primary objective | Key deliverables | Success criterion | Scope guardrail
October 2026 | Redo BCR reconstruction and establish robust blood repertoire results | Reproducible reconstruction; QC and TRUST4/MiXCR comparison; diversity/clonality/VJ/CDR3/isotype analyses beyond bcRflow; figure plan | Sample-level results and defensible repertoire metrics across both blood cohorts | Prioritise reliable comparable methods over adding many tools
November 2026 | Complete antigen-dependent work and assess structural modelling | Consolidated candidate–antigen results; small AlphaFold-Multimer pilot; initial Methods/Results draft | Traceable evidence from candidate selection to structural predictions, with limitations | Predicted structures are hypotheses, not experimental proof of binding
December 2026 | Extend workflow to tissue datasets and consolidate manuscript | Selected tissue dataset(s); QC/reconstruction/repertoire analysis; valid blood–tissue comparisons; revised draft | Coherent manuscript draft ready for supervisor review | If earlier work slips, reduce tissue scope rather than leaving all analyses incomplete
Jan-Feb 2027 | Apply and be admitted | Application sent; admission presentation (assumed late February); MAHE admission paperwork | Selected for the PhD and admitted to MAHE | Do not wait for a perfect manuscript; the January intake is the deadline
Mar-Aug 2027 | Proposal, DAC, protocol presentations, registration | DAC formed; 10-15 page proposal; MSMF presentation (ceiling 6 months after admission presentation); MAHE PPAC (ceiling 2 months later); manuscript 1 submitted | Registered with MAHE and DAC 1 held inside the coordinator ceilings | Submit to MAHE early; the PPAC date is out of your hands
Sep 2027-Aug 2028 (Year 1) | Coursework, ethics, finish Aim 2A, set up Aim 2B | 12 credits and ethics approval inside 6 months of registration; extended public-data analysis; Aim 2B protocol and partner; start recruitment; review article; DAC 2 and DAC 3 start | Coursework and ethics done; recruitment under way | Ethics approval comes before any recruitment
Sep 2028-Aug 2029 (Year 2) | Generate and analyse the Aim 2B data | Recruitment finished; RNA-seq; BCR reconstruction; repertoire-calcium score association; second conference; DAC 3-5 and progress reports | Repertoire results for about 20 patients with caveats | If recruitment is slow, cut the optional antigen-dependent work first
Sep 2029-Feb 2030 (Year 3, first half) | Papers and thesis | Manuscript 2 submitted; thesis chapters; grant groundwork; DAC 5 | Two first-author papers submitted or accepted (one may be a review) | Publications must be accepted before the synopsis
Mar-Aug 2030 | DAC 6, synopsis and thesis submission | DAC 6 permission; open synopsis presentation; Turnitin and NOC; thesis submitted (not before the minimum duration) | Thesis submitted; evaluation and viva follow | Aim 1 is parked and not part of this plan

## Weekly Check-in
Week starting | This week's 1–3 outcomes | Tasks worked on | Completed / evidence | Blockers / decisions | Next week's focus | Supervisor discussion

## Read Me
Purpose | Flexible tracker from October 2026 to thesis submission. October-December 2026 is manuscript work before PhD admission; the application starts in January 2027; later phases are broad.
October | Re-run reconstruction for GSE166780 and GSE173983; compare TRUST4 and MiXCR where useful; run repertoire analyses beyond bcRflow; document QC and statistical design.
November | Consolidate antigen-dependent analysis, prioritise candidates, run a small AlphaFold/AlphaFold-Multimer pilot if appropriate, and draft Methods/Results.
December | Select and analyse a manageable tissue RNA-seq dataset; run reconstruction and repertoire analysis; compare tissue and blood only where study designs support it; consolidate manuscript.
Documentation context | The supplied document describes GSE166780 as 24 samples across noCAD/Mild-CAD/CAD-MI and GSE173983 as 4 samples across healthy/chronic CAD. TRUST4 is the primary route; MiXCR + immunarch is a parallel route. Existing metrics include diversity, clonality, isotype, V/J usage and CDR3.
Planning rule | Target months and effort estimates are flexible planning aids. Only rows marked FIXED carry deadlines, and those come from the coordinator board and the MSMF/MAHE guidelines.
Definition of done | Each task should end with an artifact: QC report, reproducible table, figure, decision note, script or manuscript section.
Manuscript standard | Prioritise a coherent and defensible story over maximum analysis count. Agree minimum scope and claims with your supervisor.
AlphaFold caveat | Predicted structures and confidence metrics do not establish experimental antigen binding; document inputs, candidate selection and uncertainty.
Scope guardrail | If October blood analysis slips, reduce tissue dataset/candidate count rather than spreading effort across too many unfinished analyses.
Colour key | Red cells in "Deadline type" and "Latest date / rule" mark FIXED deadlines, and their task text is bold dark red. Row colours show the phase: green January-February 2027, purple March-August 2027, orange year 1, blue year 2, pink year 3.
Fixed deadlines | The ceilings are the coordinator's: admission presentation to MSMF protocol presentation 6 months; to MAHE 2 months; to DAC 1 2 weeks; DAC 2-5 within 2 years; DAC 6 to synopsis 6 months; synopsis to thesis 7 days. Other fixed items come from the guidelines. All dates are on the Key Deadlines sheet.
Assumed dates | The admission presentation date (26 February 2027) is an assumption. Change the yellow cell on Key Deadlines and every date recalculates. Planned dates leave room before each ceiling.
Effort column | For months after December, effort in days is indicative only.
Aim 1 | The agent-based model is tentative and on hold, as the supervisor asked. It appears as one On Hold row.
To confirm with the PhD office | 1) Does the 2 years on the board cover DAC 2-5, or DAC 1 to DAC 6? The plan assumes six-monthly DACs. 2) Ethics: 6 months (section 8.1.3) or 1 year (section 5)? The plan uses 6 months. 3) Can the pre-admission manuscript count as a required paper without a MAHE affiliation? 4) Are you exempt from the written test?
Workplan Chart | First worksheet: Gantt-style month-by-month diagram based on the attached PDF. Red = fixed milestones; green = pre-application/manuscript work; purple = proposal/completion; orange = Year 1; blue = Year 2; teal = ongoing requirements; grey = parked Aim 1.