## Task Tracker
ID | Month | Workstream | Task / Goal | Estimated effort (days) | Status | Definition of done / deliverable | Next action / notes
1 | October | Planning | Audit existing analysis and freeze blood-dataset sample metadata | 2 | For discussion | Verified sample sheet, group labels, inclusion/exclusion rules | Confirm counts and conditions for GSE166780 and GSE173983
2 | October | BCR reconstruction | Re-run reconstruction on GSE166780 | 5 | Not Started | Per-sample outputs, logs, tool versions, parameters and QC recorded | Compare rerun with existing TRUST4 and MiXCR outputs
3 | October | BCR reconstruction | Re-run reconstruction on GSE173983 | 3 | Not Started | Per-sample outputs, logs and QC recorded | Keep validation cohort separate
4 | October | Pipeline comparison | Compare TRUST4 and MiXCR reconstruction outputs | 4 | Not Started | Per-sample summary of productive contigs, chain recovery, QC and failures | Do not select a tool on total sequence counts alone
5 | October | Repertoire analysis | Run diversity/repertoire tools beyond bcRflow | 6 | For discussion | Reproducible sample-level metrics and figures for both cohorts | Assess diversity, clonality, V/J usage, CDR3 and isotype where supported
6 | October | Statistics | Create cross-dataset analysis table and statistical plan | 3 | Not Started | Master table, planned group comparisons and documented cohort limitations | GSE173983 is very small (n=4 total per documentation)
7 | October | Manuscript | Create manuscript skeleton and figure plan | 2 | Not Started | Working title, aims, Methods outline and planned figures | Keep claims proportionate to the public bulk RNA-seq cohorts
8 | November | Antigen-dependent analysis | Audit and consolidate existing antigen-dependent outputs | 3 | Not Started | Inventory of candidates, antigen list, pairing/structure status and gaps | Mark what is complete, needs rerunning, or is not reliable
9 | November | Antigen-dependent analysis | Prioritise candidate BCR/antibody sequences | 4 | Not Started | Transparent candidate-selection criteria and ranked candidate list | Clonal expansion is not by itself proof of antigen specificity
10 | November | Antigen-dependent analysis | Complete or refresh antigen-dependent analysis for selected candidates | 8 | Not Started | Reproducible candidate–antigen table and interpretable figures | Record antigen structure/provenance and uncertainty
11 | November | Structural modelling | Decide where AlphaFold/AlphaFold-Multimer may help | 3 | Not Started | Short methods decision note and pilot design | Check chain setup, antigen construct and complex confidence metrics
12 | November | Structural modelling | Run a small AlphaFold complex-modelling pilot | 5 | Not Started | Pilot structures and quality summary compared with existing docking | Predicted structures/confidence are not proof of binding
13 | November | Integration | Integrate repertoire, antigen and structural results | 4 | Not Started | Coherent tables/figures and explicit limitations | Identify strongest manuscript-level claims and remaining gaps
14 | November | Manuscript | Draft Methods and Results for blood-dataset work | 5 | Not Started | First complete draft of Methods and Results with figure references | Draft while results stabilise
15 | December | Tissue datasets | Identify suitable tissue RNA-seq datasets | 4 | Not Started | Dataset screening table: accession, tissue, sample size, phenotype, reads, metadata | Prefer a manageable dataset with useful metadata
16 | December | Tissue datasets | Download/process selected tissue data and run QC | 5 | Not Started | QC summaries and reproducible processing logs | Avoid expanding to many datasets
17 | December | Tissue BCR reconstruction | Run BCR reconstruction on selected tissue data | 6 | Not Started | Per-sample reconstruction outputs and comparable QC metrics | Tissue and PBMC may differ in immune-cell abundance and BCR recovery
18 | December | Tissue repertoire analysis | Run diversity/clonality analyses on tissue data | 5 | Not Started | Tissue sample-level repertoire table and core figures | Reuse metric definitions where technically appropriate
19 | December | Cross-compartment | Compare tissue and blood results where valid | 4 | Not Started | Comparison with explicit cohort/protocol caveats | Avoid pooling incompatible designs
20 | December | Manuscript | Integrate findings and prepare manuscript package | 6 | Not Started | Coherent draft, core figures, methods, results and limitations for supervisor review | Reserve time for revisions and reproducibility checks
21 | All three months | Reproducibility | Maintain run log, versions, parameters, scripts and provenance | 1 | In Progress | Every reported result traceable to code, inputs and parameters | Update after each run
22 | All three months | Supervisor check-ins | Review progress, unblock decisions and agree scope cuts | 1 | Not Started | Short decision log after each check-in | Agree early on minimum manuscript-ready scope

## Monthly Overview
Three-Month Manuscript Roadmap
Month | Primary objective | Key deliverables | Success criterion | Scope guardrail
October 2026 | Redo BCR reconstruction and establish robust blood repertoire results | Reproducible reconstruction; QC and TRUST4/MiXCR comparison; diversity/clonality/VJ/CDR3/isotype analyses beyond bcRflow; figure plan | Sample-level results and defensible repertoire metrics across both blood cohorts | Prioritise reliable comparable methods over adding many tools
November 2026 | Complete antigen-dependent work and assess structural modelling | Consolidated candidate–antigen results; small AlphaFold-Multimer pilot; initial Methods/Results draft | Traceable evidence from candidate selection to structural predictions, with limitations | Predicted structures are hypotheses, not experimental proof of binding
December 2026 | Extend workflow to tissue datasets and consolidate manuscript | Selected tissue dataset(s); QC/reconstruction/repertoire analysis; valid blood–tissue comparisons; revised draft | Coherent manuscript draft ready for supervisor review | If earlier work slips, reduce tissue scope rather than leaving all analyses incomplete

## Weekly Check-in
Week starting | This week's 1–3 outcomes | Tasks worked on | Completed / evidence | Blockers / decisions | Next week's focus | Supervisor discussion

## Read Me
Purpose | Flexible October–December 2026 tracker focused on manuscript-ready work before PhD admission.
October | Re-run reconstruction for GSE166780 and GSE173983; compare TRUST4 and MiXCR where useful; run repertoire analyses beyond bcRflow; document QC and statistical design.
November | Consolidate antigen-dependent analysis, prioritise candidates, run a small AlphaFold/AlphaFold-Multimer pilot if appropriate, and draft Methods/Results.
December | Select and analyse a manageable tissue RNA-seq dataset; run reconstruction and repertoire analysis; compare tissue and blood only where study designs support it; consolidate manuscript.
Documentation context | The supplied document describes GSE166780 as 24 samples across noCAD/Mild-CAD/CAD-MI and GSE173983 as 4 samples across healthy/chronic CAD. TRUST4 is the primary route; MiXCR + immunarch is a parallel route. Existing metrics include diversity, clonality, isotype, V/J usage and CDR3.
Planning rule | Target months and effort estimates are flexible planning aids, not fixed deadlines.
Definition of done | Each task should end with an artifact: QC report, reproducible table, figure, decision note, script or manuscript section.
Manuscript standard | Prioritise a coherent and defensible story over maximum analysis count. Agree minimum scope and claims with your supervisor.
AlphaFold caveat | Predicted structures and confidence metrics do not establish experimental antigen binding; document inputs, candidate selection and uncertainty.
Scope guardrail | If October blood analysis slips, reduce tissue dataset/candidate count rather than spreading effort across too many unfinished analyses.